## ORC2.0 Report
Project Type | Severity of Problem | Warrantable/Non Warrantable | Type of ORC | Failure Date | Problem Definition (Step-1) | Observations (Step-2) | System | Sub System | Under Analysis (Step-3) | Solution Identification & Release (Step-4) | Solution Validation & ORC Closure (Step-5) | Solution Implementation (Step-6) | Conclusion and Tracking (Step 7) | ORC Current Status | Date of ORC Creation | Date to reach at Step 2 | Date to reach at Step 3 | Date to reach at Step 4 | Date to reach at Step 5 | Date to reach at Step 6 | Date to reach at Step 7 | Time to Solution Release (days) | Time to Close the ORC (days) | Remarks
Regular | 4 | Non Warrantable | Track | 27-Dec-2020 17:49 | feed pump is fouling with Hood | feed pump is fouling with Hood | Engine |  | The Feed Pump position is not changed with respect to Front cover mounitng in 24hp & 27hp. The fouling of Hood with Feed pump could be because of non-conformance in Hood or in Assembly and to be checked by Tractor Assy team for confirmation. |  | Based on COE remarks Orc has been Closed |  |  | Step 7 | 30-Dec-2020 17:49 | 30-Dec-2020 17:50 | 31-Dec-2020 13:11 | 13-Jan-2021 16:23 | 19-Jan-2021 21:06 |  | 04-Feb-2021 14:48 | 20 | 36 | Based on COE remarks Orc has been Closed
Regular | 5 | Non Warrantable | Build | 16-04-2021 12:00:00 AM | IN YUV NXT EXPORT TRACTOR BUILD, AUX VALVE HOSES AND PIPES ARE EXCESS IN LENGTH (ALL PIPES AND HOSES) | NA | Hydraulic | HYDRAULIC LINES-FD0310 | IN DRAWING HOSE LENGTH WAS NOT AS PER 3D MODEL. | HOSE LENGTH CORRECTED IN DRAWING | As per COE comment hose length corrected in drwaing.Hence we are closing this ORC |  |  | Step 6 | 17-May-2021 23:42 | 18-May-2021 02:10 | 19-May-2021 13:00 | 28-May-2021 09:43 | 31-May-2021 11:48 | 17-Jun-2021 09:02 |  | 14 |  | As per COE comment hose length corrected in drwaing.Hence we are closing this ORC
Regular | 5 | Warrantable | Track | 27-Dec-2020 18:30 | Oil leakage observed from brake drum drain plug LH &RH side after 100 cycles of RC Test on YNXT 28 HP Tractor | Oil leakage Observed From Brake Drum Drain Plugs Both LH & RH Sides | Transmission | OIL IMMERSED BRAKE-FD0210 | There is no change in brake drum,brake assly,drain plug,oil qty,oil level in Jivo 28HP over Jivo 24HP. Complete brake assly is carryover from Jivo 24HP. There is no issue related to leakage from drain plug in Jivo 24HP. So RC test leakage from drain plug may be due to less torquing of drain plug or old drain plug fitment without precoated thread sealant. New drain plug to be fitted and torque to be applied and leakage to be checked. |  | Based on COE Remarks Orc has been closed - Carryover part |  |  | Step 7 | 28-Dec-2020 18:31 | 28-Dec-2020 18:31 | 31-Dec-2020 13:18 | 13-Jan-2021 12:56 | 18-Jan-2021 10:45 |  | 23-Jan-2021 02:29 | 21 | 26 | Based on COE Remarks Orc has been closed - Carryover part
Regular | 6 |  | Track | 23-Jan-2021 13:17 | Battery tray base plate found in bend condition on TT test tractor. | Battery tray base plate found in bend condition on TT test tractor. | Frontal-System |  |  |  | - |  |  | Obsolete | 16-Feb-2021 13:19 | 16-Feb-2021 13:19 | 17-Feb-2021 19:00 | [6 empty] | Based on COE remarks , Orc has been Obsoleted
Regular | 6 |  | Field | 05-10-2020 12:00:00 AM | Y-NXT 28 HP 4WD TRACTOR OBSERVED MORE VIBRATION ON STEERING, BONNET & FENDER . | ORC's seprated for Steering and fender aggregate. So obsolete this ORC. | Tractor-System | STEERING-FD060207 | Direction given by Gupta Sir to adopt Universal Joint to reduce vibration at steering. Needs to be transferred to Tractor System COE. It needs to be discussed with NVH team (Mr. Chavan) Pl. remove comments from under analysis field |  | - |  |  | Obsolete | 07-Oct-2020 20:03 | 08-Oct-2020 01:42 | 08-Oct-2020 22:58 | [6 empty] | ORC's seprated for Steering and fender aggregate. So obsolete this ORC.
Regular | 7 | Warrantable | Field | 13-10-2020 12:00:00 AM | TRANSMISSION OIL SEEPAGE OBSERVED FROM CLUTCH HOUSING AND SPEED HOUSING JOINT FACE. | Pls refer the attached photos - Oil seepage area | Transmission |  | ? Carry forwarded from current production tractor ? As per CPH Concurrence, No scope to work on existing parts, Refer attached mail as per Engg. Review ? Moreover, no issues in current production. ? Hence, ORC to be closed |  | As per COE confirmation, ORC closed. |  |  | Step 7 | 15-Oct-2020 08:22 | 15-Oct-2020 13:54 | 15-Oct-2020 18:36 | 09-Nov-2020 18:28 | 30-Nov-2020 21:10 |  | 02-Dec-2020 09:34 | 46 | 48
Regular | 4 | Non Warrantable | Field | 05-10-2020 12:00:00 AM | Y-NXT 28 HP TRACTOR AIR CLEANER SECONDARY ELEMENT LOOKS BULGING. | refer attached photo | Engine-Integration | AIR INTAKE SYSTEM-FD060102 | There is no uneven shape or bulging on filter element .The bulging is noticed only on the secondary element outer mesh. It is not causing any assembly issue / performance issue. Air cleaner is same as current production Yuv NXT model, So this is not to be considered as an ORC. |  | As per COE confirmation, ORC closed. |  |  | Step 7 | 07-Oct-2020 19:52 | 08-Oct-2020 01:37 | 08-Oct-2020 23:04 | 16-Oct-2020 14:35 | 19-Oct-2020 13:14 |  | 21-Oct-2020 16:51 | 12 | 14
Regular | 5 | Non Warrantable | Build | 1-Oct-2020 12:46 | Radiator hose from thermostat to radiator inlet fouling with fuel return line pipe and air cleaner. | Radiator hose from thermostat to radiator inlet fouling with fuel return line pipe and air cleaner. | Engine-Integration | COOLING SYSTEM-FD060104 | Issue is due to proto radiator assembly/hose. As per CAD lay out more than 12 mm gap observed, refer PPT attached. |  | Found ok in plant tractor. |  |  | Step 7 | 19-Oct-2020 12:47 | 19-Oct-2020 12:48 | 19-Oct-2020 18:38 | 30-Oct-2020 18:07 | 02-Nov-2020 14:13 |  | 03-Nov-2020 16:15 | 14 | 15 | Found ok in plant tractor.
Regular | 5 | Warrantable | Build | 1-Oct-2020 12:22 | Difficult to insert the scuttle in LH side due to wiring harness fouling internally. | Difficult to insert the scuttle in LH side due to wiring harness fouling internally. | Electrical |  |  |  | As Per COE & VA, drawing was updated and parts under procurment. hence we are closing the ORC. |  |  | Step 6 | 19-Oct-2020 12:22 | 19-Oct-2020 12:23 | 19-Oct-2020 18:23 | 20-Oct-2020 11:40 | 07-Dec-2020 20:06 | 08-Dec-2020 14:16 |  | 49 |  | AAs Per COE & VA, drawing was updated and parts under procurment. hence we are closing the ORC.
Regular | 6 | Non Warrantable | Tear-Down | 9-Feb-2021 10:25 | In ynxt 28 hp RC test tractor, during teardown we observed, RH side lower link mounting nut found in loosen condition. (Hand free movement) | In ynxt 28 hp RC test tractor, during teardown we observed, RH side lower link mounting nut found in loosen condition. (Hand free movement) | Hydraulic | POWER TRAIN ASSEMBLY | Thread loc to be added to avoid loosening. |  | Based on COE closure confirmation mail we are closing. |  |  | Step 7 | 10-Feb-2021 10:27 | 10-Feb-2021 10:27 | 10-Feb-2021 10:34 | 22-Feb-2021 21:54 | 01-Mar-2021 19:35 |  | 11-Mar-2021 15:06 | 19 | 29 | Based on COE closure confirmation mail we are closing.
Regular | 7 | Non Warrantable | Field | 15-02-2021 12:00:00 AM | Y NXT 28 HP TESTED WITH CAT 1 STANDARD IMPLEMENT (SPAN 683MM AND MAST HEIGHT 460MM) AND MODIFIED LOWER LINK (32 MM CHECK CHAIN MOUNTING HOLE SHIFTED TRACTOR SIDE FROM EARLIER POSITION), OBSERVED THAT IMPLEMENT HAVING 12 TO 14" SWAY EVEN THOUGH CHECK CHAIN FULLY TIGHTEN CONDITION. | WITH STANDARD CAT 1 IMPLEMENT SWAY ADJUSTMENT IS NOT POSSIBLE WITH MODIFIED CHECK CHAIN HOLE POSITION. REFER ATTACHED VIDEO AND PHOTOS. | Hydraulic | 3-POINTS LINKAGE ASSY | The new hole added at the tractor is only applicable for CAT1N implements not suitable for CAT 1 implements. |  | As per COE confirmation, ORC closed. |  |  | Step 7 | 15-Feb-2021 20:19 | 16-Feb-2021 02:24 | 16-Feb-2021 15:35 | 22-Feb-2021 22:04 | 01-Mar-2021 20:01 |  | 11-Mar-2021 12:39 | 14 | 24
Regular | 5 | Non Warrantable | Build | 16-04-2021 12:00:00 AM | IN YUV NXT EXPORT TRACTOR BUILD, UNABLE TO FIT AUX PIPE RUBBER PAD DUE TO GAP NOT AVAILABLE IN BETWEEN PIPES. | NA | Hydraulic | HYDRAULIC LINES-FD0310 | DUE TO CLAMPING RUBBER CLAMP IS SQUEEZING | PIPE ROUTING AND CLAMP DESIGN CHANGED | As per COE comment Pipe routing is changed.Hence we are closing this ORC |  |  | Step 6 | 17-May-2021 23:43 | 18-May-2021 02:12 | 19-May-2021 12:56 | 28-May-2021 10:11 | 15-Jun-2021 17:15 | 21-Jun-2021 12:23 |  | 29 |  | As per COE comment Pipe routing is changed.Hence we are closing this ORC
Regular | 7 |  | Field | 13-10-2020 12:00:00 AM | CLUSTER RPM NEEDLE FLICKERING AND MALFUNCTIONING OBSERVED. | This issue observed in two tractors. Already ORC created. (ORC-YUD1-20-000377/001-G2). ORC obsolete | Electrical |  |  |  | - |  |  | Obsolete | 15-Oct-2020 08:21 | 15-Oct-2020 13:52
Regular | 8 | Warrantable | LAB | 16-Dec-2020 12:28 | Low range lever (L2F gear) jump out issue duirng Gear train endurance test | Jumpout issue observed | Transmission |  | Various trails conducted at SEL lab and there is no co-releation wrt either rpm or torque. Tested upto 580 kgm torque in ramp up and down condition. Slip observed at 1 condition out of 7 trails during ramp down (200 Kgm). There is no change in the range section for 28 HP model only addition is 4WD. But 24 HP 4WD is under production. There is no single incidence of gear slip at customer end. Also, there is some torque fluctuation issue observed in test rig which cannot be directly related to slip. This may be a incidence and to be monitored on large numbers. |  | added 1.2mm Spacer in the Range Fork Assy and checked. ok |  |  | Step 7 | 21-Dec-2020 13:05 | 21-Dec-2020 13:05 | 23-Dec-2020 18:08 | 13-Jan-2021 17:26 | 18-Jan-2021 11:00 |  | 22-Feb-2021 12:13 | 28 | 63 | awaited for modification part

## ORC Summary
YUVRAJ
Project Name | No. of ORCs on Solution Release | Average Time to solution release (Days) | No. of ORCs on Solution Close | Average Time to close the ORC (Days)
1175-D1 | 127 | 26 | 106 | 42